## Open Timetable
Open e-Tender Timetable
Dates
The first step of the Procurement cycle is to ensure that you have identified the business need - i.e. "make or buy".
Establish suitable people to form the Tender Panel
The Lead Officer will need to create a business case and get full Departmental approval.
A Tender Record form will need to be filled in for Audit Purposes. This will be filled in with CPU guidance.
Commence evaluation report for file - To include: Make or Buy decision, Estimated spend, Initial meeting with CPU officer etc.
Prepare Tender Documents - contract requirements/Specification, schedule of work for prices, obtain insurance min requirements, financial assessment information and H&S advice.
For over £75,000 make Translation Services aware as early as possible there will be documents to be translated.
Tender Pack must be complete and Ensure ALL members of the Tender Evaluation Panel agree the documentation prior to placing advert
Prepare Advertisement - The advert will need to be bilingual for CPR exercises and contain the relevant dates. CPU can provide a sample copy of previous adverts for guidance.
Ensure that any UK Advert does not appear before the European (OJEU) and that adverts appear in the local press 28 days before the deadline for receiving requests to participate.
The UK Notice should not provide any information over and above that detailed in the European one.
If Open Procedure is used, we need to be specific enough to put off time wasters.
CPU to ensure Tender Record Form has been signed off.
xx/xx/xxxx | Advertise PIN in OJEU to notify the market of the potential forthcoming opportunity
PIN must be advertised for 35 days to benefit from reduced timescales
xx/xx/xxxx | Complete Tender documents and for Tenders over £75,000 send for Translation
Allow 3-4 weeks for Documents
to be translated
at least
28 days for Contract Procedure Rules | Lead Officer to advise Tracey Williams of forthcoming Tender requirements- to undertake a PASS/FAIL Financial Assessment
Lead Officer to advise H&S officer of forthcoming Tender requirements- to undertake a PASS/FAIL H&S Assessment
35 days for EU (at least 15 days with PIN) | Any additional information requested from Tenderers must be provided at least 6 days before the deadline of receipt of Tenders.
30 days for EU electronic tender process | Arrange for panel to meet to evaluate tenders and select suppliers asap following deadline of the return of tenders.
xx/xx/xxxx | Deadline Date
(14:00)
Arrange for panel to meet to evaluate Qualification Envelope
Advise ALL Tenderers that have not proceeded to the Evaluation Stage.
Allow 2-4 weeks | Arrange for panel to meet to evaluate the Technical and Commercial envelopes and select suppliers.
(depending on the complexity
of the tender exercise) | Evaluate technical capability & financial standing of preferred supplier using Qualification Envelope
to complete evaluation |  | Send Financial information to Tracey Williams to assess Financial Standing- PASS/FAIL response will be provided
and produce report. |  | Send Health & Safety information to the H&S Officer to assess Health & Safety: PASS/FAIL response will be provided
(including upto 2 days |  | Check Insurances
to evaluate tenders) | Complete evaluation report for file to include reasons for the selection. Including the following details:-
The name and address of the contracting authority, the subject matter and value of the contract.
The results of the qualitative selection - names of selected and rejected and reasons for selection/rejection
The reasons for the rejection of tenders found to be abnormally low.
The name of the successful tenderer and the reasons why selected. Include where possible details of subcontracting.
Where applicable the reasons why the contracting Authority has decided not to award
Where applicable the reasons why means of communication other than electronic means have been used for the submission of tenders
Ensure panel members sign the report off
XX/XX/XXXX | Advise ALL Tenderers of award decision but it is essential that you allow 10 days Voluntary/Mandatory standstill period before actually awarding the Contract.
Award decision notification must contain - the award criteria (MEAT), tenderer's score (where appropriate), winning tenderer's score (where appropriate) & name of winning tenderer.
Allow
10 days | Review evaluation report following conclusion of standstill
XX/XX/XXXX | Award Contract (should be approximately a month before Contract Commencement Date)
XX/XX/XXXX | Contract commencement date
Place within 30 days of Award | Contract Award Notice
Note on A1: Enter Tender Title in here
Note on A18: Please enter relevant date in here
Note on A21: Please enter relevant date in here
Note on A30: Please enter relevant date in here
Note on A51: Please enter relevant date in here
Note on A56: Please enter relevant date in here
Note on A58: Please enter relevant date in here