## Restricted Template
Restricted Tender Timetable
Dates
The first step of the Procurement cycle is to ensure that you have identified the business need - i.e. "make or buy".
Establish suitable people to form the Tender Panel
The Lead Officer will need to create a business case and get full Departmental approval.
A Tender Record form will need to be filled in for Audit Purposes. This will be filled in with CPU guidance.
Commence evaluation report for file - To include: Make or Buy decision, Estimated spend, Initial meeting with CPU officer etc.
Prepare specification, evaluation criteria and scoresheets. The evaluation criteria must be considered at this stage for information relating to the weightings must be included in the OJEU advert.
Prepare Tender Documents - contract requirements/Specification, schedule of work for prices, obtain insurance min requirements, financial assessment information and H&S advice.
For over £75,000 make Translation Services aware as early as possible there will be documents to be translated.
Lead Officer to advise Tracey Williams of forthcoming Tender requirements- to undertake a PASS/FAIL Financial Assessment
Lead Officer to advise H&S officer of forthcoming Tender requirements- to undertake a PASS/FAIL H&S Assessment
Lead officer to contact Julie Standeven to ascertain Insurance requirements
Prepare Tender Documents - contract requirements/Specification, schedule of work for prices
Prepare Advertisement - The advert will need to contain the relevant dates. CPU can provide a sample copy of previous adverts for guidance.
Ensure that any UK Advert does not appear before the European (OJEU)
The UK Notice should not provide any information over and above that detailed in the European one.
CPU to ensure Tender Record Form has been signed off.
xx/xx/xxxx | Advertise PIN in OJEU to notify the market of the potential forthcoming opportunity
PIN must be advertised for 35 days to benefit from reduced timescales
xx/xx/xxxx | Complete Tender documents and for Tenders over £75,000 send for Translation
Allow 3-4 weeks for Documents
to be translated
35 days
xx/xx/xxxx | Deadline for receiving completed Pre Qualification Questionnaires
Arrange meetings with panel to evaluate PQQ's and decide on list of shortlisted companies
Should allow | Prepare evaluation report with details of shortlisted companies
4 weeks
Send Financial information to Tracey Williams to assess Financial Standing- PASS/FAIL response will be provided
Send Health & Safety information to the H&S Officer to assess Health & Safety: PASS/FAIL response will be provided
Insurances
xx/xx/xxxx | Send out letters informing companies not shortlisted that they have been unsuccessful
Invite companies shortlisted from PQQ stage to Tender
Additional information requested must be supplied at least 6 days before the deadline of receipt of tenders.
40 days | Ensure Tender Evaluation scoring sheets are agreed by panel
(at least
36 days
with PIN) | Arrange for panel to meet to evaluate tenders and select suppliers asap following deadline of the return of tenders.
xx/xx/xxxx | Deadline for return of Tenders
(2pm)
Panel members to evaluate returned Tender submissions.
Allow 2-4 weeks
(depending on the complexity
of the tender exercise) | Complete evaluation report for file to include reasons for the selection. Including the following details:-
to complete evaluation | The name and address of the contracting authority, the subject matter and value of the contract.
and produce report. | The results of the qualitative selection - names of selected and rejected and reasons for selection/rejection
(including upto 2 days | The reasons for the rejection of tenders found to be abnormally low.
to evaluate tenders) | The name of the successful tenderer and the reasons why selected. Include where possible details of subcontracting.
Where applicable the reasons why the contracting Authority has decided not to award
Where applicable the reasons why means of communication other than electronic means have been used for the submission of tenders
Ensure panel members sign the report off
xx/xx/xxxx | Advise Tenderers of award decision but it is essential that you allow 10 day voluntary/mandatory standstill period before awarding the Contract.
Award decision must contain - the award criteria (MEAT), tenderer's score (where appropriate), winning tenderer's score (where appropriate) & name of winning tenderer.
Allow
10 days | Review evaluation report following conclusion of standstill
xx/xx/xxxx | Award Contract (should be approximately a month before Contract Commencement Date)
xx/xx/xxxx | Contract commencement date
xx/xx/xxxx | Contract Award Notice
within 30 days | (CPU must ensure that the original OJEU contract notice Reference number is included in the Contract Award Notice)
of Contract
Award
Note on A1: Enter Tender Title in here
Note on A22: Please enter relevant date in here
Note on A25: Please enter relevant date in here